## Sheet1
Task | Responsible | Status | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  | September
|  |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4
Initialization
Creating Use cases | Ali & Ola | Complete | bar: May Week 1
Creating Requirment specification document | The Entire Team | Complete | bar: May Week 2
Creating System architicture | Mohamad & Amal | Complete | bar: May Week 3 to May Week 4
Development
Profiling
Defining Catogries | Ola & Amal | Not started | bar: June Week 1
Creating profiles | Ali & Mohamad | Not started | bar: June Week 2 to June Week 3
Dual use system
Develope tokenization+ logging process | Ali | Not started | bar: June Week 2 to June Week 3
Develope SPARQL query | Amal | Not started | bar: June Week 3 to June Week 4
Develope Dual use metrics | Mohamad | Not started | bar: July Week 1 to July Week 3
Develope a creteria to generate quality report | Ola | Not started | bar: July Week 3 to July Week 4
Deployment
Test the system | The Entire Team | Not started | bar: August Week 2
Presenting to costumer | The Entire Team | Not started | bar: August Week 3
Fix bugs | The Entire Team | Not started | bar: August Week 4 to September Week 1
Deliver to costumer | The Entire Team | Not started | bar: September Week 3
Organisation
Communication with costumer | The Entire Team | In progress
Supervising teamwork | Ali | In progress
Preparing Documents | The Entire Team | In progress